PROGRESS REPORT #1

Campus Academic Resource Sharing Platform

Project Title:  Campus Academic Resource Sharing Platform Development

Document Version:  1.0

Project Manager:  Lian Yuxiang (1230020693)

Team Members:  Lian Yuxiang 1230020693  |  Yu Kaijie 1230020426  |  Chen Hanzhong 1230032209

Course:  System Analysis and Design

Lecturer:  Dr. CHE Pak Hou (Howard)

Date:  April 18, 2026 (Week 7)

1. Executive Summary

This is the first formal progress report for the Campus Academic Resource Sharing Platform project, covering Weeks 1-7 (March 14 – April 18, 2026). The team has completed two of the eight major deliverables on schedule: the Project Charter (Week 1) and the Requirements Analysis Document (Week 5). Stakeholder research was conducted ahead of plan, providing a solid foundation for the upcoming System Design phase. The project remains on schedule with no material risks materialized.

Key Achievements:

✅ Project Charter approved by lecturer on March 15, 2026

✅ Requirements Analysis Document v1.0 finalized on April 4, 2026

✅ User research completed: surveyed 47 students across 6 departments

✅ Trello board configured with all milestones; Git repository active with 28 commits

🔄 System Design Document drafting underway (35% complete)

2. Schedule Status

Comparison of planned vs. actual progress against the project charter milestones:

| Milestone | Planned Date | Actual Status | Variance |
| --- | --- | --- | --- |
| Project Kick-off & Team Role Confirmation | Mar 15, 2026 | Completed Mar 15 | On time ✅ |
| User Research & Stakeholder Survey | Mar 22 – Mar 28 | Completed Mar 27 | 1 day early ✅ |
| Requirements Draft v0.5 | Mar 28, 2026 | Completed Mar 28 | On time ✅ |
| Requirements Review with Lecturer | Apr 1, 2026 | Completed Apr 2 | 1 day late ⚠️ |
| Requirements Document Finalization | Apr 4, 2026 | Completed Apr 4 | On time ✅ |
| System Design Document Kick-off | Apr 7, 2026 | Started Apr 7 | On time ✅ |
| UML Class Diagram (in progress) | Apr 18, 2026 | In progress (60%) | On track 🔄 |

3. Detailed Work Completed

3.1 Project Charter

The Project Charter was finalized in Week 1 and approved by Dr. CHE Pak Hou. It defines the project as a 3-person student team practical assignment building two core modules: an optimized precise retrieval engine (feature improvement) and a points-based incentive system (new feature). The charter establishes a $10,000 HKD budget, a March 14 – June 30, 2026 timeline, and explicit scope exclusions (no backend deployment, no off-campus users, no commercialization).

3.2 User Research

Quantitative survey distributed via campus WeChat groups; 47 valid responses received. Key findings:

82% of students report 'frequently' or 'very frequently' struggling to find relevant academic resources

Average time spent searching for past papers across multiple platforms: 38 minutes per session

76% expressed willingness to upload their own materials if they received tangible rewards

Top 3 desired features (multi-select): course-code filtering (89%), quality ratings (74%), preview before download (68%)

63% would prefer a points-based system over a paid platform

Qualitative interviews (n=8): students particularly emphasized the frustration of downloading wrong-year past papers and outdated lecture notes. This validates FR-06 (multi-dimensional filter including academic year) as a top-priority requirement.

3.3 Requirements Analysis Document

The 14-page RAD v1.0 was finalized on April 4, 2026 and contains:

25 functional requirements (FR-01 to FR-25), prioritized using MoSCoW

12 non-functional requirements (NFR-01 to NFR-12) covering performance, security, usability, scalability

10 use cases with full descriptions for the 3 most critical scenarios (UC-03 Search, UC-05 Upload, UC-08 Redeem)

Context-level Data Flow Diagram and Level-1 DFD covering 7 sub-processes

Entity-Relationship Diagram identifying 8 core entities

Requirements Traceability Matrix linking each FR to use case, design component, and test case ID

ISO 29148 alignment confirmed via internal checklist

3.4 Project Management Setup

| Tool | Purpose | Setup Status |
| --- | --- | --- |
| Trello | Task tracking with 4-column Kanban (Backlog / In Progress / Review / Done) | Active — 47 cards created |
| GitHub Private Repo | Version control for all deliverables and prototype code | Active — 28 commits, 3 branches |
| Figma Workspace | Collaborative prototype design | Set up — wireframes pending |
| draw.io | UML and architecture diagrams | Active — 5 diagrams in progress |
| MySQL 8.0 Local Instance | Database design validation | Installed on team lead's machine |
| Group WeChat | Daily standup & quick coordination | Active |
| Weekly Meeting Cadence | Tuesdays 19:00 (in-person) + Friday async update | Established Week 2 |

4. Issues Encountered & Resolutions

| # | Issue | Impact | Resolution / Workaround | Status |
| --- | --- | --- | --- | --- |
| 1 | Initial survey response rate too low (8 responses in first 24h) | Risked delaying requirements finalization | Switched distribution from formal email to peer WeChat groups + offered a small thank-you gift; reached 47 responses in 5 days | Resolved ✅ |
| 2 | Disagreement on whether to include admin moderation in MVP scope | Could expand scope and delay design | Held a focused decision meeting; agreed on lightweight admin queue (FR-22) only — no full admin dashboard. Decision logged in DD-05. | Resolved ✅ |
| 3 | Lecturer feedback on Requirements Draft v0.5 came one day later than expected | Pushed final review by 1 day | Adjusted internal review buffer; no impact on overall milestone | Resolved ✅ |
| 4 | MySQL 8.0 setup conflicts with existing MySQL 5.7 on team member machine | Blocked database design validation | Used Docker container for MySQL 8.0; documented in team wiki | Resolved ✅ |

5. Risk Register Update

Updates to the risk register from the Project Charter:

| Risk ID | Risk | Original Status | Current Status | Notes |
| --- | --- | --- | --- | --- |
| R1 | Function design misaligned with real pain points | Probability: Medium / Impact: High | Probability: Low / Impact: High | User research validated proposed features — strong demand confirmed |
| R2 | Schedule delays from exam conflicts | Probability: High / Impact: Medium | Probability: Medium / Impact: Medium | Front-loaded design work before mid-term exams (May 5-12) |
| R3 | Scope creep | Probability: Medium / Impact: Medium | Probability: Low / Impact: Medium | Requirements frozen Apr 4 with formal sign-off; change requests now require lecturer approval |
| R4 | Logical flaws in points rule engine | Probability: Medium / Impact: High | Probability: Medium / Impact: High | Mitigation in progress — to be addressed in System Design Document |
| R5 | Course requirement changes | Probability: Low / Impact: Medium | Probability: Low / Impact: Low | No changes announced |
| R6 (NEW) | Mid-term exam load Week 8-10 | — | Probability: High / Impact: Medium | All exams completed by May 12; schedule lighter design work during this window |

6. Next Phase Plan (Weeks 8-13)

| Week | Date Range | Planned Deliverable | Owner |
| --- | --- | --- | --- |
| Week 8 | Apr 19 – Apr 25 | System Architecture & Module Design draft | Yu Kaijie |
| Week 9 | Apr 26 – May 2 | System Design Document v1.0 (UML, DB schema, security) | Yu Kaijie + Lian Yuxiang |
| Week 10 | May 3 – May 9 | Figma low-fidelity wireframes for all 6 screens | Chen Hanzhong |
| Week 11 | May 10 – May 16 | Figma high-fidelity prototypes (interactive) | Chen Hanzhong |
| Week 12 | May 17 – May 23 | Prototype completion + internal walkthrough; usability prep | All |
| Week 13 | May 24 – May 30 | Progress Report 2; user testing with 5 students | Lian Yuxiang |

7. Budget Status

| Category | Budgeted | Spent (Wk 1-7) | Remaining | Notes |
| --- | --- | --- | --- | --- |
| Personnel | $2,000 | $0 | $2,000 | No cash compensation; nominal allocation only |
| Tools & Software | $6,000 | $0 | $6,000 | All free-tier tools sufficient so far |
| User Research & Testing Incentives | $1,000 | $200 | $800 | Survey thank-you gifts (snacks, vouchers) |
| Contingency (10%) | $1,000 | $0 | $1,000 | Untouched |
| TOTAL | $10,000 | $200 | $9,800 | 2% utilized |

8. Lecturer Approval

Submitted to Dr. CHE Pak Hou for review.

Lecturer Signature: ________________________________   Date: ________________

Comments (if any):

_______________________________________________________________________________

_______________________________________________________________________________

_______________________________________________________________________________