PROGRESS REPORT #2

Campus Academic Resource Sharing Platform

Project Title:  Campus Academic Resource Sharing Platform Development

Document Version:  1.0

Project Manager:  Lian Yuxiang (1230020693)

Team Members:  Lian Yuxiang 1230020693  |  Yu Kaijie 1230020426  |  Chen Hanzhong 1230032209

Course:  System Analysis and Design

Lecturer:  Dr. CHE Pak Hou (Howard)

Date:  May 30, 2026 (Week 13)

1. Executive Summary

This is the second and final progress report before the project's closing phase, covering Weeks 8-13 (April 19 – May 30, 2026). The team has successfully completed five additional major deliverables: the System Design Document, both low- and high-fidelity Figma prototypes, an initial round of user testing with 5 students, and a complete database schema implemented locally in MySQL 8.0. The project enters its final phase (Weeks 14-16) with all foundational work in place. Final deliverables remaining: Test & Validation Report, Presentation, and Final Project Report.

Key Achievements (Weeks 8-13):

✅ System Design Document v1.0 finalized May 2 (Week 9)

✅ Complete UML suite: class diagram, 3 sequence diagrams, state diagram, component diagram

✅ MySQL 8.0 schema implemented and populated with synthetic test data (200 resources, 50 users)

✅ Figma high-fidelity interactive prototype completed for both core features (May 23)

✅ User testing round 1 conducted: 5 student participants, average completion rate 92%

🔄 Test & Validation Report drafting in progress (45% complete)

🔄 Presentation slide deck outline approved; final design and rehearsal in Weeks 14-15

2. Schedule Status

| Milestone | Planned Date | Actual Status | Variance |
| --- | --- | --- | --- |
| System Architecture Draft | Apr 25, 2026 | Completed Apr 24 | 1 day early ✅ |
| UML Class & Sequence Diagrams | Apr 30, 2026 | Completed Apr 30 | On time ✅ |
| System Design Document v1.0 | May 2, 2026 | Completed May 2 | On time ✅ |
| MySQL Schema Implementation | May 9, 2026 | Completed May 8 | 1 day early ✅ |
| Low-fidelity Wireframes (6 screens) | May 9, 2026 | Completed May 10 | 1 day late ⚠️ |
| High-fidelity Prototype (interactive) | May 23, 2026 | Completed May 23 | On time ✅ |
| Internal Prototype Walkthrough | May 24, 2026 | Completed May 24 | On time ✅ |
| User Testing Round 1 (n=5) | May 28, 2026 | Completed May 28 | On time ✅ |
| Progress Report 2 | May 30, 2026 | Submitting today | On time ✅ |

3. Detailed Work Completed

3.1 System Design Document (Week 8-9)

The 18-page System Design Document v1.0 was finalized on May 2 and contains:

Three-tier architecture specification (Presentation / Business Logic / Data)

9-module breakdown with responsibilities, key operations, dependencies, and FR traceability

Complete UML suite — Class Diagram (8 core classes + 4 enumerations), 3 Sequence Diagrams (Search/Download, Upload, Redeem Points), Resource State Diagram, and full Component Diagram

MySQL 8.0 database schema (8 tables) with complete CREATE TABLE statements, foreign keys, indexes, and CHECK constraints

3 critical SQL queries: relevance-ranked search, monthly leaderboard, atomic points deduction transaction

Interface Design Specifications mapping 6 UI screens to API endpoints with input validation rules

Security Design covering 9 threat categories with countermeasures and implementation details

Design Decision Log documenting 6 key architectural decisions and their rationale

3.2 Database Implementation (Week 9)

All 8 MySQL tables implemented exactly per the design schema. Test data populated:

50 synthetic user accounts with varied points balances (range: 0-450 pts)

200 resources spanning 12 course codes (e.g., BBAZ16601, BBAZ16604, BBAZ16607) and 4 academic years

1,247 download records and 320 ratings to validate aggregation queries

Search query benchmarks: 95th percentile latency = 87ms with full-text + composite index (well within NFR-01's 2-second target)

Atomic points deduction transaction tested under simulated concurrency: 0 race conditions across 1,000 parallel requests

3.3 Figma Prototype (Weeks 10-11)

The Figma prototype was developed in two stages:

Stage 1 (Week 10): Low-fidelity wireframes for 6 core screens — Search, Resource Detail, Upload, Points Dashboard, My Profile, Admin Review Queue

Stage 2 (Week 11): High-fidelity interactive prototype with realistic data, full visual design, and click-through navigation between all screens

Prototype features:

Feature Improvement (Optimized Precise Retrieval): Search with multi-dimensional filtering (course code dropdown, year, type, min rating slider); ranked results with relevance score, preview snippet, rating, download count; resource detail page with related-resources carousel

New Feature (Points-Based Incentive System): Points dashboard with balance, monthly summary, full transaction history; redemption options (50 pts → 10 downloads, 100 pts → 7-day pin); leaderboard widget showing top 20 contributors of the month; in-app notification on points-earning events

Cross-feature: Upload flow with metadata form and admin review notification; rating widget on resource detail page that triggers points award sequence

3.4 User Testing Round 1 (Week 13)

Five undergraduate students (3 BBA, 2 from other faculties; 3 male, 2 female) participated in 30-minute moderated usability sessions on May 28. Each participant completed 6 tasks while thinking aloud; sessions were screen-recorded with consent.

| Task | Completion Rate | Avg. Time (s) | Major Issues Identified |
| --- | --- | --- | --- |
| T1: Register and log in | 5/5 (100%) | 47s | None |
| T2: Find a specific course's past paper using filters | 5/5 (100%) | 62s | 1 user missed the 'Year' filter location initially — fixed by adding visual emphasis |
| T3: Upload a resource and complete metadata | 4/5 (80%) | 138s | 1 user couldn't find the file dropzone — fixed by adding a 'Browse files' button |
| T4: View points balance and transaction history | 5/5 (100%) | 23s | Positive feedback — 'very clear' |
| T5: Redeem 50 points for download credits | 5/5 (100%) | 41s | None — confirmation dialog was praised |
| T6: Rate a downloaded resource | 4/5 (80%) | 55s | 1 user clicked star without entering comment — clarified the comment is optional |
| OVERALL | 92% avg. | — | 3 minor issues, all addressed in design refinements |

User satisfaction ratings (1-5 scale):

Ease of finding resources: 4.4 / 5.0  (target: ≥4.0 ✅)

Clarity of points system: 4.2 / 5.0  (target: ≥4.0 ✅)

Visual design appeal: 4.6 / 5.0

Likelihood of using if launched: 4.8 / 5.0

Net Promoter Score (would recommend to peers): +60 (very strong)

4. Issues Encountered & Resolutions

| # | Issue | Impact | Resolution | Status |
| --- | --- | --- | --- | --- |
| 5 | Mid-term exam load slowed Figma work in Week 10 | Wireframes 1 day late | Pre-loaded prototyping into Week 9 evenings; recovered in Week 11 | Resolved ✅ |
| 6 | Initial relevance score formula gave too much weight to popular but outdated resources | Risk of incorrect search results | Adjusted weights (40/30/30 → kept) + added recency factor through year filter; documented in DD-03 | Resolved ✅ |
| 7 | User Testing Participant 3 dropped out 1 day before session | Risked sample size below 5 | Recruited backup participant from team's network within same demographic profile | Resolved ✅ |
| 8 | Figma free-tier collaboration limit (3 editors) reached briefly | Slowed mid-week | Rotated editor seats during work sessions; final prototype consolidated in single file | Resolved ✅ |
| 9 | Discovered ambiguity in FR-14 (free download policy) | Could mis-implement points economy | Held mini-clarification meeting; updated FR-14 wording — '3 free downloads per day reset at midnight'; communicated to all team | Resolved ✅ |

5. Quality Metrics

| Metric | Target | Actual | Status |
| --- | --- | --- | --- |
| Functional requirement coverage in prototype | ≥95% | 100% (25/25 FRs covered) | Exceeded ✅ |
| Search response time (p95) | <2,000 ms | 87 ms (database) / ~350 ms (full prototype) | Far exceeded ✅ |
| User testing completion rate | ≥90% | 92% | Met ✅ |
| User satisfaction (avg) | ≥4.0/5 | 4.4/5 | Exceeded ✅ |
| Use case test coverage in design | 100% of UCs traced | 100% (10/10 UCs) | Met ✅ |
| Git commit cadence | ≥5/week | Avg. 8.4/week | Exceeded ✅ |

6. Final Phase Plan (Weeks 14-16)

| Week | Date Range | Deliverable | Owner |
| --- | --- | --- | --- |
| Week 14 | May 31 – Jun 6 | Apply user testing fixes; complete Test & Validation Report draft v0.5 | All / Lian Yuxiang |
| Week 14 | May 31 – Jun 6 | Build Presentation slide deck v0.5; first rehearsal | Lian Yuxiang + Yu Kaijie |
| Week 15 | Jun 7 – Jun 13 | User Testing Round 2 (n=5); finalize Test & Validation Report v1.0 | Chen Hanzhong |
| Week 15 | Jun 7 – Jun 13 | Final presentation slide deck v1.0; full team rehearsal x3 | All |
| Week 15 | Jun 13 | DELIVER: 30-min Live Presentation + Test & Validation Report | All |
| Week 16 | Jun 14 – Jun 20 | Compile Final Project Report (integrate all deliverables, reflection) | All |
| Week 16 | Jun 20 | DELIVER: Final Project Report v1.0 to Moodle | Lian Yuxiang |
| Closing | Jun 21 – Jun 30 | Final Project Package (compress all artifacts, GitHub archive, Trello export) | Lian Yuxiang |

7. Budget Status (Cumulative)

| Category | Budgeted | Spent (Wk 1-13) | Remaining | Notes |
| --- | --- | --- | --- | --- |
| Personnel | $2,000 | $0 | $2,000 | Nominal — no cash compensation |
| Tools & Software | $6,000 | $0 | $6,000 | All free-tier; no paid software needed |
| User Research & Testing Incentives | $1,000 | $520 | $480 | Wk 7 surveys ($200) + Wk 13 user testing ($320 in food/voucher gifts) |
| Contingency (10%) | $1,000 | $0 | $1,000 | Untouched — held for Round 2 testing if needed |
| TOTAL | $10,000 | $520 | $9,480 | 5.2% utilized |

8. Risk Register Update

| Risk ID | Risk | Status (Wk 7) | Status (Wk 13) | Notes |
| --- | --- | --- | --- | --- |
| R1 | Function-pain-point misalignment | Low / High | Low / Low | User testing scores 4.4+ confirm strong fit |
| R2 | Schedule delays from exams | Medium / Medium | Resolved ✅ | Mid-terms passed without schedule impact |
| R3 | Scope creep | Low / Medium | Low / Low | Frozen requirements held |
| R4 | Logical flaws in points engine | Medium / High | Low / High | Atomic transaction validated under concurrent load |
| R5 | Course requirement changes | Low / Low | Low / Low | — |
| R6 | Mid-term exam load | High / Medium | Resolved ✅ | Closed |
| R7 (NEW) | Live demo failure during presentation | — | Medium / High | Mitigation: pre-record backup screencast; test laptop+projector setup before presentation |
| R8 (NEW) | Last-minute lecturer feedback requiring rework | — | Low / Medium | Buffer Week 16 explicitly reserved for rework |

9. Lecturer Approval

Submitted to Dr. CHE Pak Hou for review.

Lecturer Signature: ________________________________   Date: ________________

Comments (if any):

_______________________________________________________________________________

_______________________________________________________________________________

_______________________________________________________________________________