Project Charter

Project Title: Campus Academic Resource Sharing Platform Development Project

Prepared by: Lian Yuxiang (Project Lead)

Project Team: 连宇翔 1230020693, 郁凯杰 1230020426, 陈瀚中1230032209

Date: March 15, 2026

1. Project Purpose & Business Case

This project is a core practical assignment for the System Analysis and Design course, delivered by a 3-person student team. It directly addresses the high-frequency pain points of college students widely discussed on Douyin and Xiaohongshu: exam review materials, past papers and course notes are scattered across multiple platforms, high-quality academic resources for the same university and major are hard to retrieve, second-hand study materials are often resold at inflated prices with unguaranteed authenticity, and there is no standardized channel for exam Q&A and homework assistance.

This platform will build a standardized academic resource sharing system for college students, with two core modules: optimized precise retrieval for campus learning materials, and a points-based incentive system for academic mutual assistance. It aims to create a positive closed loop for campus resource co-construction and sharing, while enabling the project team to master the full-process practical methods and tool applications of system analysis and design.

1.1 Feature Composition (Course Requirement Mapping)

Per the BBAZ16604 course requirement that 3-student teams deliver "1 feature improvement + 1 new feature", the two core modules are formally classified as follows:

Feature 1 — Improvement: Optimized Precise Retrieval Module

This feature improves on the existing fragmented academic resource discovery experience that students currently rely on (WeChat group searches, paid third-party platforms, peer-to-peer messaging from upperclassmen). It introduces structured multi-dimensional filtering by Course Code, Academic Year, Resource Type, and minimum Rating threshold; a composite relevance ranking formula (40% match accuracy + 30% download popularity + 30% average rating); preview snippets to reduce mistaken downloads; and personal search history. The improvement target is a 60% gain in retrieval efficiency vs current channels (per Section 2 objectives).

Feature 2 — New Feature: Points-Based Incentive System

This is a new feature not present on any existing campus resource platform used by MUST students. It introduces a points economy with five action types (upload approval +10, download received +2, rating received +1, download cost -5, daily free download tier +0); two redemption options (50 pts → 10 extra downloads; 100 pts → 7-day resource pinning); a monthly campus leaderboard ranking the top 20 contributors; and a complete points transaction audit trail with running balance. The new-feature target is an 80% increase in voluntary sharing willingness (per Section 2 objectives).

2. Project Objectives

- Complete the design and prototype development of two core modules (optimized academic resource retrieval, points-based mutual assistance management) by the end of the semester, with 100% coverage of functional requirements.

- Achieve a 95% completion rate of core business processes in user testing, with a 60% improvement in user satisfaction on resource retrieval efficiency compared to traditional channels.

- Fully deliver all course-required outputs, including two progress reports, a 30-minute project presentation, and a final report, targeting a final course score of 85 or above.

- Master core tools and methodologies required by the course, including Git/GitHub for version control, MySQL for database management, and Trello for project management.

- Reduce students' time cost of obtaining campus academic resources by 70%, increase willingness to share high-quality content by 80%, and achieve an overall user satisfaction score of 4.0/5 or above for core functions.

3. Project Scope

In Scope

- Full requirement research and analysis for the platform, including pain point research on Douyin/Xiaohongshu, questionnaire surveys and in-depth interviews with college students, in compliance with ISO 29148 requirements engineering standards.

- System architecture design, points incentive rule engine design, UML modeling, and MySQL database structure design for core modules, in compliance with ISO 12207 software lifecycle specifications.

- Development of high-fidelity interactive prototypes for core modules, covering full business processes including resource upload, precise retrieval, campus Q&A, points earning/redemption, and content review.

- Submission of two progress reports as required by the course, detailing project progress, outcomes, and challenges.

- Preparation and delivery of a 30-minute project presentation to demonstrate project outcomes.

- Compilation of a comprehensive final report covering the full project process, requirement analysis, system design, and prototype outcomes.

- Full version control of project documents and design files via Git/GitHub, and database design and management via MySQL.

Out of Scope

- Full back-end API development and online deployment of the platform (only interface design specifications for core functions will be provided).

- Support for outdated operating systems (iOS 14 and earlier, Android 8.0 and earlier).

- Development of functions unrelated to campus academic resource sharing, such as campus food delivery, social forums, and educational administration inquiry.

- Long-term operation, commercialization, and technical maintenance support after project delivery.

- Function development and service support for off-campus users.

4. Key Deliverables

1.  Requirement Analysis Document: Detailed user requirement analysis, functional/non-functional requirements, and points incentive rule design, completed by Week 5 (April 4, 2026).

2.  System Design Document: System architecture, database structure, rule engine design, and interface design, completed by Week 9 (May 2, 2026).

3.  High-Fidelity Interactive Prototype: Functional prototype covering all core business processes, completed by Week 12 (May 23, 2026).

4.  Progress Reports: Two progress reports submitted in Week 7 (April 18, 2026) and Week 13 (May 30, 2026) respectively.

5.  Presentation Materials & Live Demo: Presentation slides and 30-minute live function demo, completed by Week 15 (June 13, 2026).

6.  Test & Validation Report: Usability test results, requirement compliance verification, and optimization records, completed by Week 15 (June 13, 2026).

7.  Final Project Report: Comprehensive report summarizing the full project process and outcomes, completed by Week 16 (June 20, 2026).

8.  Final Project Package: Complete project documents, design source files, and prototype files, submitted by June 30, 2026 (end of the semester).

5. Stakeholders

Project Sponsor

Dr. CHE Pak Hou (Howard) – Course Lecturer, with final approval authority for the project plan and final evaluation of project outcomes.

Project Manager

Lian Yuxiang 1230020693 – Responsible for overall project planning, team coordination, schedule control, risk management, and daily communication with the lecturer and teaching assistant.

Project Team (3 Members)

- Lian Yuxiang 1230020693: Requirements Analyst, responsible for user research, full lifecycle requirement management, and Requirement Analysis Document compilation.

- Yu Kaijie 1230020426: System Designer, responsible for system architecture design, UML modeling, MySQL database design, and points rule engine development.

- Chen Hanzhong 1230032209: Prototype & Documentation Lead, responsible for high-fidelity prototype development, full project document management, report compilation, and presentation material production.

Key Stakeholders

- Course Teaching Assistant: High Influence / Medium Interest – Provides technical guidance, document feedback, and participates in phased project reviews.

- On-campus Student Users: Medium Influence / High Interest – Core target users of the platform, providing requirement input and participating in user research and prototype testing.

- University Student Union/Academic Department: Medium Influence / Medium Interest – Provides practical business requirements for campus academic scenarios and participates in function and rule reviews.

- Peer Project Teams: Low Influence / Low Interest – Provide peer review feedback during the project presentation.

6. Assumptions

- Each team member can commit no less than 8 hours per week to the project, with no long-term absence or withdrawal from the team.

- All required tools and software (Git/GitHub, MySQL, Trello, Figma, etc.) are accessible for free with no permission or network restrictions.

- The lecturer and TA can provide effective guidance and feedback within 3 working days at key project milestones.

- Sufficient on-campus students can be recruited for user research and prototype testing, with a valid questionnaire recovery rate of no less than 80%.

- Core user requirements can be accurately identified and fully covered through the requirement analysis process, with no major business logic omissions.

- No major changes to course project requirements, grading criteria, or submission deadlines during the project lifecycle.

7. Constraints

- Budget: Total approved project budget is $10,000; all spending must be within the approved budget, with no overspending.

- Timeline: March 14, 2026 – June 30, 2026 (full semester); all deliverables must be submitted by the course-specified deadlines with no delays.

- Resources: Fixed team size of 3 students, with no additional human resource support.

- Technical: Mandatory use of Git/GitHub for version control and MySQL for database management; free project management and prototyping tools are permitted.

- Compliance: All platform designs must comply with national cybersecurity and personal information protection laws and regulations, as well as university campus management rules.

8. High-Level Risks & Mitigation

1.  Risk: Function design misalignment with real student pain points from inadequate user research → Probability: Medium / Impact: High → Owner: Lian Yuxiang → Mitigation: Targeted research on Douyin/Xiaohongshu pain points, multi-round user reviews for timely adjustments.

2.  Risk: Schedule delays from team members’ exam schedule conflicts → Probability: High / Impact: Medium → Owner: Lian Yuxiang → Mitigation: Reserve exam week buffer time, front-load core tasks, and adjust workload promptly.

3.  Risk: Scope creep from unplanned requirement changes → Probability: Medium / Impact: Medium → Owner: Lian Yuxiang → Mitigation: Freeze requirements after formal review, only approve changes with full team and lecturer confirmation.

4.  Risk: Logical flaws in the points rule engine breaking the business loop → Probability: Medium / Impact: High → Owner: Yu Kaijie → Mitigation: Multi-round logic reviews, prepare alternative plans, and seek lecturer guidance for technical issues.

5.  Risk: Project impact from unexpected changes to course requirements or grading criteria → Probability: Low / Impact: Medium → Owner: Lian Yuxiang → Mitigation: Closely follow course announcements, communicate regularly with the lecturer to confirm requirements, and adjust the project plan accordingly.

9. Milestone Schedule

Project Kick-off & Team Role Confirmation: March 15, 2026

Requirements Finalization & Progress Report 1 Submission: April 4, 2026

System Design Finalization & Approval: April 18 , 2026

Prototype Development Complete & Progress Report 2 Submission: May 9, 2026

Testing & Optimization Finalization: May 16, 2026

Project Presentation & Final Report Submission:May 16, 2026

10. Budget Summary

Total Approved Budget: $10,000

Budget Breakdown:

- Personnel Cost: $2,000

- Tools & Software Cost: $6,000

- User Research & Testing Incentive Cost: $1,000

- Contingency (10% of Base Cost): $1,000

- Total: $10,000

11. Approval & Signatures

This charter formally authorizes the project and gives the Project Manager the authority to apply organizational resources within the approved scope and budget.

Project Sponsor: _______________________________ Date: _____________

Project Manager: _______________________________ Date: _____________

Project Team Member Confirmation:

1.  ___________________________ Date: _____________

2.  ___________________________ Date: _____________

Additional Approver: __________________ Date: _____________